## Setup Database
Sr.No. | Cost Code 1 | Section Name | [5 empty] | System SetUP
1 | A | Excavation
Sr.No. | Cost Code 2 | Sub Section Name | [5 empty] | System SetUP
2 | 1 | Foundations
Sr.No. | Cost Code 1 | Cost Code 2 | Cost Code 3 | Item No. |  |  |  | System SetUP
3 | A | 1 | a | A1a
3 | A | 1 | b | A1b
Sr.No. | Item No. | BOQ Item Detail Description | Item {Short Name} |  |  |  |  | System SetUP
4 | A1a | xxxxxxxx | xx
Sr.No. | Unit | [6 empty] | System SetUP
5 | Cum
Sr.No. | Item No. | Unit | [5 empty] | System SetUP
6 | A1a | Cum
Sr.No. | Building Name | [6 empty] | System SetUP
7 | Add Field
Sr.No. | Building Name | Item No. | Unit | Rate |  |  |  | System SetUP
8 | From Dropdown #7 | From Dropdown #6 | Automatic per #6 | Add Field
Sr.No. | Building Name | Item No. | Unit | Tender Quantity |  |  |  | System SetUP
9 | From Dropdown #7 | From Dropdown #6 | Automatic per #6 | Add Field
Sr.No. | Building Name | Item No. | BOQ Item Detail Description | Rate | Tender Quantity | Unit |  | REPORT - 1
Sr.No. | Building Name | Item No. | Item {Short Name} | Rate | Tender Quantity | Unit |  | REPORT - 2
Sr.No. | Component | [6 empty] | System SetUP
9 | Add Field | eg - Footing / Beam
Sr.No. | Tag | [6 empty] | System SetUP
10 | Add Field | eg PB 1, PB2, F1, F2
Sr.No. | Running Bill | RA Bill Date | [5 empty] | System SetUP
10 | Add Field | Add Field | RA1, RA2, RA3, RA4
Sr.No. | Building Name | Item No. | Component | Tag | Grid | Grid | Notes | No | Length | Breadth | Depth | Quantity | Unit | Running Bill | Database - SOQ
| From Dropdown #7 | From Dropdown #6 | From Dropdown #9 | From Dropdown #10 | text Field | text Field | text Field | text Field | text Field | text Field | text Field | Caculation | Automatic per #6 | Automatic per #10
Example 1 | [6 empty] | Nos | 2 | - | - | - | 2 | Ea
Example 2 | [6 empty] | Length | 2 | 3 | - | - | 6 | rmt
Example 3 | [6 empty] | Area | 2 | 3 | 4 | - | 24 | sqm
Example 4 | [6 empty] | Volumne | 2 | 3 | 4 | 5 | 120 | cum
Sr.No. | Running Bill | Building Name | Item No. | Component | Quantity | Unit | Rate | Amount | RA Bill Date | LOCK ITEMS | [5 empty] | Database - Cost by RA Bill
| Automatic Databse SOQ | From Dropdown #7 | From Dropdown #6 | From Dropdown #9 | Caculation - Summary from SOQ | Automatic per #6 | Add Field | Rate * Qty | Automatic per #11 | Generate Uniq Code
SECURITY BUILDING | [15 empty] | Report - 4
Item No. | Item {Short Name} | Unit | Tender Quantity | Quantity | Quantity | Quantity | Rate | Amount | Amount | Amount
|  |  |  | Prev. | This | Total |  | Prev. | This | Total
|  |  |  | Program for RA1+2+3 | Ra4 (Last Ra) | Prev + This |  | Program for RA1+2+3 | Ra4 (Last Ra) | Prev + This
Note on E8: Author: Get created combining the three cost codes
Note on C18: Author: From Unit Database #5

## Sampel Setup Database
Sr.No. | Description | Item {Short Name} | Qty. | Unit | Rate | Amt
A) | EARTH WORK :
1a. | Earthwork in excavation in foundations, trenches, Rain water gutter etc. in all classes of soil /Soft murrum except rock upto a depth of 1.5 meter including dewatering, shoring and strutting if required, refilling the trenches by excavated earth including Compaction up to 95% standard proctor density, spreading the surplus earth within Plot boundary and compacting it etc. complete as per instruction of Engineer-in-charge. | Excavation up to 1.5 Mtr depth | 40 | CUM | 50 | 2000
2 | Filling in ground/Plinth /trenches etc. with selected (non- expansive) earth brought from outside plot boundary, spread in layer of 150 mm to 230 mm thickness to achieve required level, slope / gradient and compacted to 95% Standard Proctor Density including transportation cost, royalty etc. complete. | Filling with earth brought from outside | 75 | CUM | 125 | 9375
3 | Providing and filling sand of approved quality in floor, sides of cable trench and below cable trench, machine foundation, foundation pits in layers of 150mm thickness and compacted to 95% relative density including watering, ramming, consolidating etc. completed as directed by Engineer-in-charge. | P & Filling Sand | 5 | CUM | 500 | 2500
4 | Providing and laying 230mm thick dry rubble packing including filling interstices with sand \ hand crushed metals well packed in line and level, rolling with Power \ Hand Roller, etc. complete. | P & L 230mm thk Rubble Soiling | 40 | CUM | 1200 | 48000
5 | Removal of surplus excavated materials not required for backfill shall be deposited in areas outside plot boundary by mechanical means upto lead of 3 KM as directed by Engineer-in-charge including loading, unloading & spreading in layers as per requirement of Engineer-in-charge. | Removal of Surplus excavated earth | 10 | CUM | 25 | 250
|  |  | TOTAL RS. |  |  | 62125
B) | CONCRETE :
1 | Providing and laying M7.5 grade (1:4:8) Plain Cement Concrete with 40mm down size graded metal for foundation below footings, floor and raft, drain and trenches, including centering, shuttering as required, laying, spreading, ramming, consolidating, curing and finishing top surface rough or smooth as per instructions of Engineer-in-charge. | P & L P.C.C. ( 1:4:8 ) | 20 | CUM | 2500 | 50000
b) | -Do- as above but for P.C.C (1:2:4) using 20mm down size graded metal. | P & L P.C.C. ( 1:2:4 ) | 5 | CUM | 3200 | 16000
2 | Providing and laying controlled reinforced Cement Concrete of M20 grade with 20mm down size graded crushed stone aggregate including scaffolding, opening, recesses, chamfering, finishing top surfaces vibrating, machine mixing tamping, curing (excluding centering and shuttering) etc.complete as per the specifications, drawings and instruction of Engineer - in- charge (excluding cost of reinforcement) for all elements of concrete
Note: Mix Design shall be got approved from the Consultant.
a. | In Foundation and upto Plinth/ Finished floor level (FFL). | P & L RCC M20 upto Plinth/FFL | 30 | CUM | 3500 | 105000
b. | -Do- as above but above Plinth level/ FFL upto +4.50m level. | P & L RCC M20 above Plinth/FFL upto 4.5mt | 30 | CUM | 3800 | 114000
3 | Extra over item no. 2 above for use of RCC M-25 grade at all levels. | Extra over item no. 2 above for use of RCC M-25 grade at all levels. | 60 | CUM | 50 | 3000
4 | Supplying & placing in position reinforcement for all type of RCC structures including cleaning, decoiling, cutting, bending to required shape and lengths, binding as per drawing and details, binding with 16 SWG black soft annealed binding wire supplying and straightening, placing with proper cover block, support chairs, overlaps, spacers, etc.complete in all respect as directed. Payment will be made as on length basis (actual or theoretical as per drg. whichever is less) and converted into weight by using standard IS coefficient (rolling margins, wastages, couplings, welded joints, spacer bars, stays, hangers, annnealed steel wire or other methods of binding and placing shall not be measured and not paid separately. Only authorised laps and chairs shall be measured and paid)
a. | High Yield Deformed Bar Reinforcement conforming to IS-1139 or Cold Twisted bar, TOR steel / TMT / or Equivalent) Reinforcement conforming to IS-1786. - Grade of Reinforcement Steel shall be- Fe500/Fe500D |  | 6 | MT | 35000 | 210000
5 | Providing and erecting in position form work, shuttering and boxing using plywood / steel shuttering materials of approved quality for all type of concrete elements vertical, horizontal or inclined including scaffolding, stagging, fasteners, nails, wires, keeping in position till concrete is laid and members have acquired required strength, removal thereafter, applying shuttering oil etc. complete as directed by Engineer-in-Charge.
a. | In Foundation and upto Plinth/ Finished floor level (FFL). | P & Erecting form work up to plinth | 150 | SQM | 180 | 27000
b. | -Do- as above but above Plinth level/ FFL upto +4.0 m level. | P & erecting form work above plinth | 350 | SQM | 210 | 73500
|  |  | TOTAL RS. |  |  | 598500
C) | MASONRY WORK :
1 | Providing and constructing brick masonry in CM 1:6 (1 Cement and 6 Coarse sand) at all level & depth with approved brick having minimum crushing strength of 35 KG / Sqcm. including scaffolding, racking out joints, curing, watering etc., comp. (for walls, steps, chambers, drain, pillar, column, butresses, parapet, galabid, etc.)
a. | -Do- as above for foundations and upto plinth level / Finish Floor Level | P & C Brickmasonary upto Plinth/FFL | 25 | CUM | 2500 | 62500
b. | -Do- as above but above Plinth level/ FFL upto +4.0 m level. | P & C Brickmasonary above Plinth upto 4.0mt | 50 | CUM | 2800 | 140000
2 | Providing and constructing 115mm thick partition wall and parapet at all height in cement mortar 1:4 (1 part of cement and four part of sand) including scaffolding, racking out joints, reinforcement of 2 Nos. 8mm dia bar at every 4th layer and watering etc. complete as directed. (steel shall be payable separately as per relevant item) | P & C 115mm thk Brick Partition Wall | 25 | SQM | 225 | 5625
|  |  | TOTAL RS. |  |  | 208125
D) | FINISHING :
1 | Providing and applying 6mm thick smooth cement finish plaster in C.M. 1:4 (one cement, two fine sand and two coarse sand) to ceiling, pattas, on RCC surfaces including scaffolding, curing, finishing smooth etc. complete at all levels as directed. | P & A 6mm thk Smooth Cement Plaster at all heights | 145 | SQM | 115 | 16675
2 | Providing and applying 12mm thick smooth cement plaster at all heights in C.M. 1:6 to walls, beams, column, drain, bends, moulds, grooves, pattas and all brick and RCC surfaces including raking of joints, scaffolding, curing finishing smooth etc complete. The plaster shall be rubbed with "Iron Plate" till the surface shows cement paste in line level complete as directed. | P & A 12mm thk Smooth Cement Plaster at all heights | 350 | SQM | 150 | 52500
3 | Providing and applying 18 mm thick sand faced cement plaster at all heights in two layers; first layer of 12 mm with CM 1:6 and second layer 6 mm thick with CM 1:4 rough finished with using sponge, on all types of concrete/brick surfaces, including providing & adding liquid water proofing admixture of "conplast X4211c of fosroc or approved equivalent of "sika" make as per manufacturer's specification, making grooves, as per detail including scaffolding, curing etc. complete. | P & A 18mm thk Sandface Plaster | 265 | SQM | 170 | 45050
0
4 | Providing and applying two or more coats of Oil bound washable distemper of "Asian or Berger" make,and of approved colour and shade including one coat of primer, brooming down and cleaning the surfaces, finishing of holes and depressions including scaffolding and stagging at all levels/heights with all labour and materials, etc. complete at all levels. | P & A two Coats of Oil Bound Washable Distemper | 145 | SQM | 90 | 13050
0
5 | Providing and applying three or more coats Acrylic Premium Emulsion paint of "Asian or Berger" make,and of approved colour and shade one coat of primer, brooming down and cleaning the surfaces, finishing of holes and depressions including scaffolding and staging of all levels with all labour and material etc. complete at all levels. |  | 350 | SQM | 130 | 45500
0
0
6 | Providing and applying two or more coats, of "Apex weather proof exterior emulsion paint" (Asian paint make) of approved shade to give good and even shade over plaster, brick / concrete surfaces at all levels as per instructions of the engineers-in-charge including scaffolding, cleaning, washing the surface etc. complete at all levels. |  | 265 | SQM | 185 | 49025
0
7 | Providing & filling the chasis (Zarri), upto 150mm wide, made for fixing electrical and other utility conduits in Brick/Concrete surfaces with C.M. 1:4 including cleaning, making the surface good to match with existing wall/concrete, curing etc complete. |  | 20 | RMT | 90 | 1800
0
8 | Providing and making grooves 12 x 12mm in cement plaster for architectural elevation as well as at junction of beams/Columns with brick masonry as per drawing & instructions of the Engineer-In-Charge at all levels/ heights above or below Final Ground Levels. |  | 10 | RMT | 35 | 350
0
|  |  | TOTAL RS. |  | 0 | 223950
0
E) | PAVIOR |  |  |  | 0
| NOTES : |  |  |  | 0
i) | Procurement of white cement and colour pigment is in scope of contractor. |  |  |  | 0
ii) | Use approved quality of black granite of premium quality. |  |  |  | 0
iii) | Basic rate of materials indicated in the items are for quoting only. If material approved with purchase rate higher or lower than basic rate than difference between basic rate & purchase rate shall be payable or recoverable. |  |  |  | 0
iv) | Quoted rates includes protecting and cleaning all finished surfaces and also rounding of corners, edges and junctions of floor/wall with skirting and dado. |  |  |  | 0
0
1 | Providing and laying 25mm thick polished machine cut edge blue Kota Stone of size 600 x 450 mm for flooring & skirting including laying on 25mm thick C.M (1:4) mix including finishing joint with matching colour cement, cutting the stones to require sizes, making holes for pipes, rubbing and machine polishing the top surfaces after laying etc. complete as per instruction of engineer in charge. Basic rate of kota stone shall be Rs.400/ sqm. |  | 40 | SQM | 1300 | 52000
0
2 | Providing and fixing 300 mm x 450 mm x 7.3 mm thick Ceramic tiles of "NITCO" or "BELL" make in flooring & skirting & dado including laying over 12mm thick C.M. 1:3 mix bed to proper level or slope, with providing & fixing 3mm wide spacers where ever required (as per drawing) & filling the joints with epoxy joint filler of approved colour & shade at all levels and all heights etc complete. (Rate shall be inclusive of backing coat of cement plaster wherever required) Basic rate of tiles shall be Rs.450/ sqm. |  | 10 | SQM | 1000 | 10000
0
3 | Providing and fixing 1st quality screen printed glazed tiles 300/450mm x300/ 450mm size of "NITCO" or "BELL" or approved equivalent make, colour and shade in dado including backing coat of cement plaster 12mm thick in C.M. 1:3 mix, providing & fixing 3mm wide spacers where ever required (as per drawing) & filling the joints with epoxy joint filler of approved colour & shade at all levels and all heights etc complete. Basic rate of tiles shall be Rs.400/ sqm |  | 45 | SQM | 985 | 44325
0
4 | Providing and laying 25mm thick Kota Stone slabs in treads, risers, Landing, side skirting of steps, laid on 12mm (average) thick cement mortar 1:3 (1 cement : 3 coarse sand) and finishing joint with white cement slurry mixed with pigment to match the shade of the slabs, including cutting to required size, rubbing and polishing, making half round nosing for treads etc complete. |  | 10 | SQM | 1200 | 12000
0
5 | Providing & fixing 18 /20mm thick one side polished stone min. 1500 mm long for 300 mm wide Door / window Jams & sill with half round edge polish/moulding on one side and edge polish on other side including laying on 20mm thick C.M.(1:4) bedding (Stone may be cut into two pieces of required size and fixed in staggered manner including required overlapping with adhesive material as required, measurement shall be per running meter of total laid length only) |  |  |  | 0
a. | 18 /20mm thick one side polished black granite.(basic rate - 2000/- sqm ) |  | 100 | RMT | 1400 | 140000
0
6 | Providing and fixing machine polished 20mm thick granite platform over 25 mm thk. kota stone supports including providing opening for oval shaped wash basin, bibcock etc including Half round moulding, filling joints, making connection for water inlet, etc. complete as directed. |  | 2 | SQM | 4900 | 9800
|  |  | 0 |  | 0
7 | Providing and fixing 18 mm thick granite partition. All the edges shall be cut on machine and polished on both side as well as on edge with rounded top including chasing the brick work & finish with cement mortar 1:3, including curing etc. complete. |  | 2 | SQM | 3675 | 7350
0
8 | Providing & laying Manglore tiles & ridge of required thickness & size of approved make, colour as approved by Architects over 12 - 30 mm (average ) thick bed of CM 1:4 jointing with cement slurry including pointing with cement mixed with pigment of matching colour, painting with three coats of synthetic enamal paint & coat of primer etc. at all levels/heights. |  | 135 | SQM | 845 | 114075
0
9 | Providing and laying both side polished Granite slabs 18 to 20 mm thick for Writing platform to be fixed on wall including making & filing jari with cement mortar 1:3 (1 cement : 3 coarse sand) if required including cutting to required size, chamfering as required, moulding and polishing complete. (measurement shall be taken as per net plan area of granite slab fixed.) (Basic Rate -2000/- sqm) |  | 5 | SQM | 4900 | 24500
0
10 | Providing & laying 1st quality of Marbogranite vitrified tiles of 600/800 x 600/800mm size of approved make, colour and shade by Architects in flooring / skirting over 20 mm thick bed of CM 1:3 with 3mm wide spacers & filling the joints with epoxy joint filler of approved colour & shade at all levels and all heights etc complete. (Basic Rate of Tiles shall be Rs. 750/ Sqm.) |  | 75 | SQM | 1645 | 123375
0
11 | Providing and laying single side polished black Granite cladding 12mm thick for column, walls, bends on front side with necessary adhesives including cutting to required size , chamfering / moulding as per drawing and polishing etc complete. |  | 5 | SQM | 3480 | 17400
0
|  |  | TOTAL RS. |  | 0 | 554825
0
F) | DOOR/ WINDOW WORK : |  |  |  | 0
0
1 | Providing, fabricating and fixing in position aluminum door including frame in single/ double wings shutters using "Jindal" make aluminum sections with approved colour anodizing (15 microns), supplying and fixing minimum 5.0 mm plain glass, having clear vision including sealing the gap between frame & plaster with sealant of approved make, all fixtures and fastening and fitting such as hinges, handles, barrel bolts chromium plated brass Yale lock, handrop bolt for locking of shutters etc. all as per drawing/ manufacturing specification & direction of Engineer-in- Charge. |  |  |  | 0
i. | Door outer frame - 63.50 x 38 x 2.5 mm @ 1.116 Kg/mt JINDAL code no. 19552 OR section no. 20001 for partition door frame |  |  |  | 0
ii. | Shutter top rail - 47.62 x 44.45 x 3.18 @ 1.50 Kg/m - Jindal Code no. 19503 |  |  |  | 0
iii. | Shutter vertical style (hinge side) - 47.62 x 44.45 x 2.82mm @ 1.293 Kg/m - Jindal code no. 19502 |  |  |  | 0
iv. | Shutter vertical style - 47.62 x 44.45 x 3.18mm @ 1.505 Kg/m - Jindal code no. 19501 |  |  |  | 0
v. | Lock rail - 83.5 x 44.45 x 2.40mm @ 1.679 Kg/m Jindal code no. 19525 |  |  |  | 0
vi. | Shutter bottom rail - 85 x44.45 x 2.70mm @ 1.843 Kg/m Jindal code no. 19563 |  |  |  | 0
vii. | Glazing clip - 19.0 x 17.30 x 0.90mm @ 0.124 Kg/m. Jindal code no. 19360 |  |  |  | 0
0
a. | -DO- As above but with partly glazed shutter at top using 5mm thick plain glass & partly panelled shutter at bottom using 9mm thick prelaminated particle board (exterior grade) of approved manufacturer with decorative lamination on both sides of shutter. |  | 5 | SQM | 5228 | 26140
0
b. | -DO- As above but with fully panelled shutter using 9mm thick prelaminated particle board with decorative lamination on one side & balancing lamination on other side. |  | 5 | SQM | 5228 | 26140
0
|  |  | 0 |  | 0
2 | Providing, fabricating and fixing in position aluminum windows and ventilator using "Jindal" make aluminum sections with approved colour anodizing (15 microns), Supplying and fixing 5.5mm thick clear float glass including sealing the gap between frame & plaster with sealant of approved make, all fixtures and fastening, fittings such as hinges, handles, tower bolts (concealed) etc. all as per drawing / manufacturing specification. & direction of Engineer in charge. |  | 0 |  | 0
a. | Two track window using following sections: |  | 25 | SQM | 5300 | 132500
i) | Bottom frame - 92.6 x 32 x 2.0mm thick @ 1.805Kg/m Jindal code no. 20712 |  | 0 |  | 0
ii) | Top & side frame - 82.8 x 44.0 x 2.0mm thick @ 1.429 Kg/m Jindal Code no. 20713 |  | 0 |  | 0
iii) | Shutter bottom frame - 64.00 x 25.4 x 1.8mm thick @ 1.051 Kg/m - Jindal code no. 20857 |  | 0 |  | 0
iv) | Shutter top & side frame - 50.8 x 25.4 x 2.0mm @ 1.006 Kg/m Jindal code no. 20715 |  | 0 |  | 0
v) | Shutter interlocking frame - 50.8 x 25.4 x 2.0mm thick @ 1.229 SKg/m. jindal code no. 20711 |  | 0 |  | 0
b. | Fixed type |  | 5 | SQM | 5300 | 26500
i) | Outer frame: 63.5 x 38.1 x 3.18 @ 1.777 Kg/m Jindal code no. 20005 |  | 0 |  | 0
ii) | Middle member with double groove: 63.5 x 38.10 x 3.18 @ 1.924 Kg/m Jindal code no. 20004 |  | 0 |  | 0
iii) | Glazing clips: 19.0 x 17.3 x.0.9 @ 0.124 Kg/m Jindal code no. 19360 |  | 0 |  | 0
|  |  | 0 |  | 0
c. | Louvered type |  | 2 | SQM | 5300 | 10600
i) | Outer frame: 38.1 x 25.4 x 2.41 @ 0.764 Kg/m |  | 0 |  | 0
ii) | Suitable aluminum channel |  | 0 |  | 0
0
3 | Providing and fixing Hydraulic door closure of "OZONE or DORMA" approved ISI make into position etc. complete as directed. |  | 2 | NO. | 2875 | 5750
0
|  |  | TOTAL RS. |  | 0 | 227630
0
G) | MISCELLANEOUS : |  |  |  | 0
0
1 | Providing and fixing 24 gauge chicken wire mesh at the junction of masonry work and RCC work or on any other place as directed including fixing with nails, raw/ plugs etc. complete at all heights before applying plaster. |  | 20 | SQM | 80 | 1600
0
2 | Providing and injecting chemical emulsion for Pre - Constructional Antitermite (Conforming IS: 6313 part : ii )1971 and creating a chemical barrier under and around the column pits, wall trenches, basement excavation, top surface of plinth filling, jundtion of wall and floor, along with external perimeter of the building and expansion joint, around jundction of pipes and conduits with soil/rock etc. all complete works shall be carried out by a licenced contractor as per manafacturers specification by using chemical Biflex TC with 0.05 % a.i concentration, by spraying hand pump etc. complete as diected and specified. This treatment sholud be done by specilaised agency approval for which should be obtained from project manager before finliasing the agency. (Plinth area of the building at ground floor only shall be measured & paid). Unit rate shall be inclusive of gurantee of 7 year and submitting gurantee on stamp paper. |  | 110 | SQM | 55 | 6050
|  |  | 0 |  | 0
3 | Providing and laying average 120 mm thick water proofing treatment over flat RCC roof & to vertical surface of parapet wall upto 300 mm high as per drawing shall be done including fillets at junction of roof & vertical walls with M-15 grade concrete finished with 12 mm thick CM 1:4 (only plan area to be taken for measurement purpose ) as per following layer |  | 115 | SQM | 760 | 87400
| Applying & grouting a slurry coat of neat cement using 2.75kg/sqm of cement admixed with proprietary water proofing compounds conforming to IS: 2645 over the RCC slab including cleaning the surface before treatment. |  | 0 |  | 0
| Laying Cement concrete using broken bricks/brick bats 25mm to 100mm size with 50% of cement mortar 1:5 (1 cement : 5 coarse sand) admixed with proper water proofing compound conforming to IS:2645 to req slope & treating similarly the adjoining wall upto 300mm height including rounding of junctions of walls & slabs. |  | 0 |  | 0
0
| After two days of proper curing applying a second coat of cement slurry admixed with proprietary water proofing compound conforming to IS:2645. |  | 0 |  | 0
| Finishing the surface with 20mm thick jointless cement mortar of mix 1:4 (1Cement : 4 Coarse sand) admixed with proprietary water proofing compound conforming to IS :2645 and finally finishing the surface with trowel with neat cement slurry and making of 300 x 300 mm Square. |  | 0 |  | 0
| The whole terrace so finished shall be flooded with water for a minimum period of two weeks for curing and for final test. All above operations to be done in order and as directed and specified by the Engineer-In-charge. |  | 0 |  | 0
0
4 | Providing, fixing in position PVC pipe 4kg/sqcm pressure and damping with wall, necessary jointing of pipe elbows, bends etc. at any floor, connecting drain spout with pipe with all cost of materials labours complete. |  |  |  | 0
a. | 110 mm dia. |  | 15 | RMT | 375 | 5625
0
5 | Supplying, fabricating, erecting 1 mtr. High M.S Pipe railing at all levels of flush welded construction with smooth uniform curves and bends of 40 mm N.B medium class M.S Pipe at top & verticals spaced not more than 1.5 mtr. C/C & 25 N.B medium class M.S Pipe mid rail, base plate, anchor bolts, 100 x6 mm toe plate etc. including painting with two coats of synthetic enamel paint of approved make, quality and shade over a coat of zinc chromate primer (rate shall include fixing hand rail to steel platform, staircase or concrete members) Measurement shall be per Rmt of railing & not for individual pipe. supply of all steel is in scope of contractor. |  | 15 | RMT | 1580 | 23700
0
|  |  | TOTAL RS. |  | 0 | 124375
0
H) | SANITARY WORK: |  |  |  | 0
| NOTE: |  |  |  | 0
| Serial no. for Sanitary wares given for "Cera" make. If such makes are not available in market, than use "Parryware /Hindware/Serabird /Orient" brand with equivalent serial no. after approval of owner/engineer in charge. All plumbing fixtures shall be of " Kingston/ Gem / Techno/Parko" make unless otherwise specified. |  |  |  | 0
0
1 | Providing and fixing White Orissa type W.C. pan of "CERA" make (no. 2071) of size 580 x 440 mm with `P' or 'S' trap (No. 9002). The rate shall include concealed flush cock with necessary inlet connection upto flush cock and outlet connections in concealed manner, cutting and making good floor etc. complete. |  | 1 | NO. | 6500 | 6500
|  |  | 0 |  | 0
2 | Providing and fixing glazed earthenware White Wall Hung European type standard WC pan of "Cera" make (no. 2045) with pair of CI chair brackets, white solid plastic seat cover (no. 2345), CP brass hinges and rubber buffers, 25mm concealed Flush cock, 15mm concealed stop cock of "Jaquar" make, C.P. flanges, necessary fastner & fixing, cutting and making good the walls and floors where required, all complete. |  | 2 | NO. | 20100 | 40200
|  |  | 0 |  | 0
3 | Providing & fixing in position S.S. towel rail of approved make of 600mm length, 20mm dia. With a pair of brackets or flanges fixed to wall with necessary screws, plugs etc. all as specified & directed. | P & F S.S.Towel Rail_600mm Length | 2 | NO. | 1500 | 3000
4 | Providing and fixing C.P brass toilet paper holder of approved make. | P & F C.P.Brass Toilet Paper Holder | 2 | NO. | 1200 | 2400
5 | Providing & fixing Stainless steel liquid soap holder cum dispenser of approved make to the wall with necessary brackets, screws, washers, plugs etc. all as specified & directed. | P & F S.S. Liquid Soap Holder | 1 | NO. | 2500 | 2500
6 | Providing and fixing Oval wash basin (size 550 x 460 mm of "cera" make (no. 1005) of white colour standard quality including including inlet and outlet connections, Pillar cock, stop cock, angle cock of approved quality, C.P. Brass bottle trap, CI Brackets CP brass waste coupling, cutting & making good the wall, etc. complete. (All plumbing fixtures shall be of "Jaquar" make). | P & F Oval Wash Basin_550x460mm | 2 | NO. | 7500 | 15000
7 | Providing and fixing in position best quality approved make 6mm beveled edge mirror mounted on 12mm thick water proof plywood backing and hardwood beading alround and mirror fixed to the backing with 4 nos of CP cap screws & washers including fixing the mirror to the wall with necessary screws, plugs & washers etc. complete. | P & F 6mm beveled edge mirror | 3 | SQM | 2500 | 7500
8 | Providing and fixing C.P. brass bib cock of approved make of 15mm dia including Teflon tap, leak proof fittings, etc. | P & F C.P.Brass Bib Cock | 2 | NO. | 1400 | 2800
9 | Supplying, fixing & testing PVC floor trap (6 Kg/Sq cm) with solvent cement joints, including all the fittings. The work shall include wall chase and making good the same in cement mortar complete to the satisfaction of engineer-in-charge. |  |  |  | 0
a. | P Trap 100 mm | P/F PVC Floor Trap_100mm dia | 3 | NO. | 660 | 1980
10 | Providing & fixing S.S. Three piece jali 150x150mm incl. Cement rendering, etc. complete | P & F S.S.Three piece Jali | 3 | NO | 330 | 990
11 | Providing, fixing & testing pipes for water supply of following diameters at all levels, including with all necessary fixtures like bends, elbow etc. Quoted rate shall be inclusive of excavation and refilling the trenches / cutting floors & wall / making hole in RCC/ Brick work / making groove/ clamping finishing, jointing & sealing the same with sealant, making good after work etc. including hydro test complete as directed by engineer in charge. |  | 0 |  | 0
| -Do- as above item no. 11 for U-PVC (SCHEDULE- 40) Plumbing pipe as per ASTM - D - 1785 of "Supreme or Finolex" make & of nominal diameter of pipe. |  |  |  | 0
a. | 15mm dia. pipe | P/F UPVC Pipe_15mm dia | 15 | RMT | 135 | 2025
b. | 25mm dia pipe. | P/F UPVC Pipe_25mm dia | 10 | RMT | 235 | 2350
12 | Supplying, fixing & testing PVC pipe (6 Kg/Sq cm) in floor and on wall confirming to IS 4985 for waste connections with solvent cement joints, including all the fittings laid under floor concealed in wall, encasing with PCC etc., The work shall include wall chase and making good the same in cement mortar complete to the satisfaction of engineer-in-charge. Encasing PCC shall be paid under relavent item. |  |  |  | 0
a. | 100mm dia. | P/F & T PVC Pipe 6kg/Sq.cm for 100mm dia | 10 | RMT | 540 | 5400
b. | 75mm dia | P/F & T PVC Pipe 6kg/Sq.cm for 75mm dia | 5 | RMT | 375 | 1875
13 | Providing and fixing Square mouth Stone ware Gully Trap grade "A" 100 x100 size "P" type of approved quality, including 230mm thick brick masonary chamber of 300 x300mm clear inside in C.M. (1:5) plastered on both sides in C.M. (1:3) with C.I cover not less than 4.5 kg and frame not less than 2.7 kg. to fixed in Cement concrete 1:2:4 including necessary excavation to required depth,1:4:8 bedding of 150mm thick etc. complete. | P & F Stoneware Gully Trap "P" type | 2 | NO. | 4050 | 8100
14 | Providing and fixing 100 mm dia. C.I.Vent pipe upto 1m length with Cowl piece for Air Ventilator with jali wire mesh including 25mm deep seal lead joint. etc. complete. | P & F 100mm dia C.I.Vent Pipe | 2 | NO. | 940 | 1880
15 | Providing and fixing approved make double type coat & hat hooks with flanges, fixed to wall / shutter etc. with necessary screws, washers and plugs all as specified & directed. | P & F Double type Coat Hat Hook | 2 | NO. | 565 | 1130
|  |  | 0 |  | 0 | 105630
I) | PILE WORK : |  |  |  | 0
1 | Labour charges for making bore for under ream piles including making bulb as per specifications with bentonite \ temporary casing, if required in all type of soils including spreading of bored material within plot boundary as per instruction of Engineer-in-charge. The Bore will have a depth of 5.0 mtr. (Depth of Boring payable shall be taken as per actual i.e. with respect to GL ) |  |  |  | 0
i) | 300mm dia. | Boring of Underream Piles_300mm dia upto 5.0mt | 50 | RMT | 300 | 15000
ii) | 450mm dia. | Boring of Underream Piles_450mm dia upto 5.0mt | 50 | RMT | 600 | 30000
2 | Providing and laying M-25 grade mix for RCC under ream pile including machine mixing, placing the concrete with chute, consolidating, curing etc. complete as directed by Engineer-in-charge. (Payment shall be made for quantity worked out on theoretical basis ( i.e. as per drawing, with respect to cut-off only) (Reinforcement shall be paid under relevant item) | P & L M-25 for RCC underream Pile | 15 | CUM | 4650 | 69750
|  |  | TOTAL RS. |  |  | 114750

## Measurement Database
D1_A
Builindg Componets List
D2_A
Grid Name
D3_A
Bill Nos

## MS_Report Need
Client: SHAILY Engineering Plastic Ltd. | [11 empty] | Bill No: | 10th
Building Name:-SECURITY BUILDING
Item no. | Tender Item | Location | Particular#1 | Grid | Grid | Level | Particular #2 | Particular#3 | No | Length | Breadth | Depth | Quantity | Unit | Bill | Submital Date | Lock Date
From Setpup Database | From Setpup Database | From -MS Database | From -MS Database | From -MS Database | From -MS Database | "Text Box" | "Text Box" | "Text Box" | "Text Box" | "Text Box" | "Text Box" | "Text Box" | Programmed per Tender Item's Unit | From Setpup Database | From -MS Database | Calendar | Calendar
Ref: | Drg No:1865-SEC-C01-SH1-R1/ Dt: 12-06-20 Layout of Foundation for Security Building & Experience Centre
A-1.a | Excavation up to 1.5 Mtr depth | F1/C2,C3,C4,C5,C6,C10,C11,C12,C16,C17,C18 | Footing | B to F/ D to F | 1/2&3 | Below G.L | L=1.3+2*0.075 | B=1.5+2*0.075 | 11 | 1.45 | 1.65 | 1.5 | 39.4763 | CUM
A-1.a | Excavation up to 1.5 Mtr depth | F2/C14,C15 | Footing | B & C | 3 | Below G.L | L=1.7+2*0.075 | B=1.7+2*0.075 | 2 | 1.85 | 1.85 | 1.5 | 10.2675 | CUM
A-1.a | Excavation up to 1.5 Mtr depth | F4/C8 | Footing | B | 2 | Below G.L | L=1.75+2*0.075 | B=1.5+2*0.075 | 1 | 1.9 | 1.65 | 1.5 | 4.7025 | CUM
A-1.a | Excavation up to 1.5 Mtr depth | F5/C9 | Footing | C | 2 | Below G.L | L=1.65+2*0.075 | B=1.5+2*0.075 | 1 | 1.8 | 1.65 | 1.5 | 4.455 | CUM
A-1.a | Excavation up to 1.5 Mtr depth | [6 empty] | H=1.5 | 15 |  |  | This bill | 58.9012 | CUM
Adopted item factory A-1.b | Excavation 1.5m to 3.0m depth | F1/C2,C3,C4,C5,C6,C10,C11,C12,C16,C17,C18 | Footing | B to F/ D to F | 1/2&3 | Below G.L |  | D=100.987-98.2-1.5 | 11 | 1.45 | 1.65 | 1.287 | 33.8706 | CUM
Adopted item factory A-1.b | Excavation 1.5m to 3.0m depth | F2/C9,C14,C15 | Footing | B & C | 3 | Below G.L |  |  | 2 | 1.85 | 1.85 | 1.287 | 8.8095 | CUM
Adopted item factory A-1.b | Excavation 1.5m to 3.0m depth | F4/C8 | Footing | B | 2 | Below G.L |  |  | 1 | 1.9 | 1.65 | 1.287 | 4.0347 | CUM
Adopted item factory A-1.b | Excavation 1.5m to 3.0m depth | F5/C9 | Footing | C | 2 | Below G.L |  |  | 1 | 1.8 | 1.65 | 1.287 | 3.8224 | CUM
Adopted item factory A-1.b | Excavation 1.5m to 3.0m depth | [6 empty] | H=2+.075-1.5 | 15 |  |  | This bill | 50.5373 | CUM
B-1 | P & L P.C.C M7.5 (1:4:8) | F1/C2,C3,C4,C5,C6,C10,C11,C12,C16,C17,C18 | Footing | B to F/ D to F | 1/2&3 | Below G.L | L=1.3+2*0.075 | B=1.5+2*0.075 | 11 | 1.45 | 1.65 | 0.075 | 1.9738 | CUM
B-1 | P & L P.C.C M7.5 (1:4:8) | F2/C14,C15 | Footing | B & C | 3 | Below G.L | L=1.7+2*0.075 | B=1.7+2*0.075 | 2 | 1.85 | 1.85 | 0.075 | 0.51337 | CUM
B-1 | P & L P.C.C M7.5 (1:4:8) | F4/C8 | Footing | B | 2 | Below G.L | L=1.75+2*0.075 | B=1.5+2*0.075 | 1 | 1.9 | 1.65 | 0.075 | 0.23512 | CUM
B-1 | P & L P.C.C M7.5 (1:4:8) | F5/C9 | Footing | C | 2 | Below G.L | L=1.65+2*0.075 | B=1.5+2*0.075 | 1 | 1.8 | 1.65 | 0.075 | 0.22275 | CUM
B-1 | P & L P.C.C M7.5 (1:4:8) | [7 empty] | 15 |  |  | This bill | 2.9451 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | F1/C2,C3,C4,C5,C6,,C10,C11,C12,C16,C17,C18 | Footing | B to F/ D to F | 1/2&3 | Below G.L | L=1.300 | B=1.500 | 11 | 1.3 | 1.5 | 0.2 | 4.29 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | [5 empty] | Trapezoidal part | v=H/3(A1+A2+sqrt(A1*A2)) | 11 | 0.21972 |  |  | 2.4169 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | [5 empty] | A2 = L'xB' |  |  | 0.33 | 0.45 | 0.25
B-2.a | P & L R.C.C M20 in Foundation up to plinth | F2/C14,C15 | Footing | B & C | 3 | Below G.L | L=1.700 | B=1.700 | 2 | 1.7 | 1.7 | 0.25 | 1.445 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | [5 empty] | Trapezoidal part | v=H/3(A1+A2+sqrt(A1*A2)) | 2 | 0.31631 |  |  | 0.63262 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | [5 empty] | A2 = L'xB' |  |  | 0.33 | 0.55 | 0.25
B-2.a | P & L R.C.C M20 in Foundation up to plinth | F4/C8 | Footing | B | 2 | Below G.L | L=1.75 | B=1.500 | 1 | 1.75 | 1.5 | 0.25 | 0.65625 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | [5 empty] | Trapezoidal part | v=H/3(A1+A2+sqrt(A1*A2)) | 1 | 0.2914 |  |  | 0.2914 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | [5 empty] | A2 = L'xB' |  |  | 0.33 | 0.55 | 0.25
B-2.a | P & L R.C.C M20 in Foundation up to plinth | F5/C9 | Footing | C | 2 | Below G.L | L=1.65 | B=1.5 | 1 | 1.65 | 1.5 | 0.25 | 0.61875 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | [5 empty] | Trapezoidal part | v=H/3(A1+A2+sqrt(A1*A2)) | 1 | 0.26915 |  |  | 0.26915 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | [5 empty] | A2 = L'xB' | PB Bottom RL |  | 0.33 | 0.45 | 0.25
B-2.a | P & L R.C.C M20 in Foundation up to plinth | F1/C2,C3,C4,C5,C6,C10,C11,C12,C16,C17,C18 | Pedestal | B to F/ D to F | 1/2&3 | PB botttom | 230*350 | 100.784 | 11 | 0.23 | 0.35 | 2.059 | 1.8232 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | F2/C14,C15 | Pedestal | B & C | 3 | PB botttom | 450*450*230 | Part A | 2 | 0.23 | 0.45 | 2.009 | 0.41586 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | F2/C14,C15 | Pedestal | B & C | 3 | PB botttom | 450*450*230 | Part B | 2 | 0.22 | 0.23 | 2.009 | 0.20331 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | F4/C8 | Pedestal | B | 2 | PB botttom | 450*230 |  | 1 | 0.45 | 0.23 | 2.009 | 0.20793 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | F5/C9 | Pedestal | C | 2 | PB botttom | 230*350 |  | 1 | 0.23 | 0.35 | 2.009 | 0.16172 | CUM
B-2.a | P & L R.C.C M20 in Foundation up to plinth | [10 empty] | This bill | 13.4321 | CUM
B-3 | Extra over item no. 2 above for use of RCC M-25 grade at all levels. | [10 empty] | Same Qty asper Item No:B-2.a | 13.4321 | CUM
B-3 | Extra over item no. 2 above for use of RCC M-25 grade at all levels. | [10 empty] | This bill | 13.4321 | CUM
B-5.a | P & erecting form work up to plinth | F1/C2,C3,C4,C5,C6,C10,C11,C12,C16,C17,C18 | Footing | B to F/ D to F | 1/2&3 | Below G.L | L=(1.3+1.5)*2 |  | 11 | 5.6 |  | 0.2 | 12.32 | SQM
B-5.a | P & erecting form work up to plinth | F2/C14,C15 | Footing | B & C | 3 | Below G.L | L=(1.7+1.7)*2 |  | 2 | 6.8 |  | 0.25 | 3.4 | SQM
B-5.a | P & erecting form work up to plinth | F4/C8 | Footing | B | 2 | Below G.L | L=(1.75+1.5)*2 |  | 1 | 6.5 |  | 0.25 | 1.625 | SQM
B-5.a | P & erecting form work up to plinth | F5/C9 | Footing | C | 2 | Below G.L | L=(1.65+1.5)*2 |  | 1 | 6.3 |  | 0.25 | 1.575 | SQM
B-5.a | P & erecting form work up to plinth | F1/C2,C3,C4,C5,C6,C10,C11,C12,C16,C17,C18 | Pedestal | B to F/A/ D to F | 1/ 2/2&3 | PB botttom | L=(0.23+0.35)*2 |  | 11 | 1.16 |  | 2.059 | 26.2728 | SQM
B-5.a | P & erecting form work up to plinth | F2/C14,C15 | Pedestal | B & C | 3 | PB botttom | L=(0.45+0.45)*2 | Part A & B | 2 | 1.8 |  | 2.009 | 7.2324 | SQM
B-5.a | P & erecting form work up to plinth | F4/C8 | Pedestal | B | 2 | PB botttom | L=(0.45+0.23)*2 |  | 1 | 1.36 |  | 2.009 | 2.7322 | SQM
B-5.a | P & erecting form work up to plinth | F5/C9 | Pedestal | C | 2 | PB botttom | L=(0.23+0.35)*2 |  | 1 | 1.16 |  | 2.009 | 2.3304 | SQM
B-5.a | P & erecting form work up to plinth | [10 empty] | This bill | 57.4879 | SQM

## Report -Abstract_Formate
Client :- SHAILY Engineering Plastics Ltd.
Work:- Civil Work for Factory Building & Associated works at Chandrapura -Halol. | [8 empty] | RA Nos. :- | 10th
SECURITY BUILDING
Item no. | D e s c r i p t i o n | Unit | Quantity |  |  |  | Rate | Amount ( INR)
|  |  | BOQ | Prev. | This | Total |  | Prev. | This | Total
A-1.a | Excavation Upto 1.5m depth | CUM | 40 |  | 58.9012 | 58.9012 | 174 | 0 | 10248.8175 | 10248.8175
Adopted item factory A-1.b | Excavation 1.5m to 3.0m depth | CUM |  |  | 50.5373 | 50.5373 | 189 | 0 | 9551.5445 | 9551.5445
B-1 | P & L PCC M 7.5 (1:4:8) | CUM | 20 |  | 2.9451 | 2.9451 | 3300 | 0 | 9718.7062 | 9718.7062
B-2.a | P & L R.C.C M20 in Foundation up to plinth | CUM | 30 |  | 13.4321 | 13.4321 | 4450 | 0 | 59773.0377 | 59773.0377
B-3 | Extra over item no. 2 above for use of RCC M-25 grade at all levels. | CUM | 60 |  | 13.4321 | 13.4321 | 215 | 0 | 2887.9108 | 2887.9108
B-4.a | P & Fixing Reinforcement Steel | MT | 6 |  | 2.1129 | 2.1129 | 54000 | 0 | 114095.736 | 114095.736
B-5.a | P & erecting form work up to plinth | SQM | 150 |  | 57.4879 | 57.4879 | 470 | 0 | 27019.3224 | 27019.3224
TENDER ITEM TOTAL AMT OF SECURITY BUILDING [ B ] | [6 empty] | Rs. | 0 | 233295.0752 | 233295.0752
UNDER GROUND TANK
Item no. | D e s c r i p t i o n | Unit | Quantity |  |  |  | Rate | Amount ( INR)
|  |  | BOQ | Prev. | This | Total |  | Prev. | This | Total
A-1 | Excavation Upto 1.5m depth | CUM | 105 | 243.645 |  | 243.645 | 174 | 42394.23 | 0 | 42394.23
A-1.b | Excavation 1.5m to 3.0m depth | CUM | 105 | 243.645 |  | 243.645 | 189 | 46048.905 | 0 | 46048.905
A-1.c | Excavation 3.0m to 4.5m depth | CUM | 55 | 227.4108 |  | 227.4108 | 236 | 53668.9429 | 0 | 53668.9429
A-3 | P& L 90 to 63 mm crushed stones 200/250mm thk. | CUM | 20 | 38.5942 |  | 38.5942 | 1898 | 73251.8485 | 0 | 73251.8485
B-1.b | P & L PCC M10 | CUM |  | 16.7801 |  | 16.7801 | 3375 | 56632.8375 | 0 | 56632.8375
B-2.a | P & L R.C.C M25 in foundations and super structure at all levels | CUM | 50 | 173.3131 |  | 173.3131 | 4750 | 823237.0825 | 0 | 823237.0825
B-3 | Extra over item no. 2 above for use of RCC M-30 grade at all levels. | CUM | 50 | 159.9966 |  | 159.9966 | 230 | 36799.218 | 0 | 36799.218
B-4.b | P & Fixing Reinforcement Steel | MT | 5 | 18.785 |  | 18.785 | 54000 | 1014387.678 | 0 | 1014387.678
B-5.a | P & erecting form work in foundations and super structure at all levels | SQM | 285 | 826.7365 |  | 826.7365 | 510 | 421635.615 | 0 | 421635.615
C-4 | P & enjection type water proofing | SQM |  | 290.46 |  | 290.46 | 515 | 149586.9 | 0 | 149586.9
C-6 | Providing and fixing in position 230mm wide x 5mm thick PVC water stop | RMT | 120 | 194.4 |  | 194.4 | 330 | 64152 | 0 | 64152
C-8 | Providing and fixing CI medium duty Manhole Cover with frame | KG | 75 | 150 |  | 150 | 105 | 15750 | 0 | 15750
C-9 | Providing and fixing 100 mm dia CI vent pipe up to 1.0 m length | NO | 1 | 0 |  | 0 | 945 | 0 | 0 | 0
Adopted Rate Factory C-1.b | P & C Brick work above plinth | CUM |  | 11.3204 |  | 11.3204 | 4200 | 47545.554 | 0 | 47545.554
Adopted Rate Factory D-2 | P & A 12mm thk smooth cement plaster | SQM |  | 70.0935 |  | 70.0935 | 275 | 19275.7125 | 0 | 19275.7125
Adopted Rate Factory D-4 | P & A 18mm thk sandface plaster | SQM |  | 389.355 |  | 389.355 | 350 | 136274.25 | 0 | 136274.25
Adopted Rate Factory E-8.a | Providing & fixing one side polished stone min. 1500 mm long for 300 mm wide Door / window Jams & sill with half round edge For 18 /20mm thick Marble | RMT |  | 27.38 |  | 27.38 | 1030 | 28201.4 | 0 | 28201.4
Adopted Rate Factory E-8.b | Providing & fixing one side polished stone min. 1500 mm long for 300 mm wide Door / window Jams & sill with half round edge For 18 /20mm thick black granite | RMT |  | 48 |  | 48 | 1400 | 67200 | 0 | 67200
Adopted Rate Factory E-11 | S & L 40mm thk IPS floor finish | SQM |  | 87 | 25.58 | 112.58 | 400 | 34800 | 10232 | 45032
Adopted Item Rate Factory G-2.a | P and fixing PVC Rain water Pipe110mm dia | RMT |  | 3.25 |  | 3.25 | 375 | 1218.75 | 0 | 1218.75
Adopted Rate Factory H-1.a | Supply structural steel like angles,channels,beams,plates etc. | MT |  | 1.868 | 0.11176 | 1.9798 | 51000 | 95268 | 5699.8875 | 100967.8875
Adopted Rate Factory H-1.b | Fabrication & instalation structural steel like angles,channels,beams,plates etc. | MT |  | 1.3722 | 0.083822 | 1.456 | 25000 | 34304.6154 | 2095.5469 | 36400.1623
Adopted Rate Factory H-4.a | Supply inserts like angles,channels,beams,plates etc. | MT |  | 0.037296 |  | 0.037296 | 51000 | 1902.1113 | 0 | 1902.1113
Adopted Rate Factory H-4.b | Fabrication & instalation inserts like angles,channels,beams,plates etc. | MT |  | 0.027972 |  | 0.027972 | 25000 | 699.3056 | 0 | 699.3056
adopted Item Rate Security G-3 | P&L Brick bat coba waterproofing 120mm avg thk | SQM |  | 42.5216 |  | 42.5216 | 760 | 32316.416 | 0 | 32316.416
Adopted Rate Factory G-18.b | P/F anchor fasteners 16mm diax150mm long | Nos. |  |  | 4 | 4 | 225 | 0 | 900 | 900
Adopted Rate Factory G-19.a | P/F anchor fasteners chemical 20mm diax150mm long | Nos. |  |  | 5 | 5 | 950 | 0 | 4750 | 4750
Adopted Rate Factory G-25 | S,F & Erecting 1.0 Mtr high MS Pipe Railing | RMT |  |  | 6.2625 | 6.2625 | 1580 | 0 | 9894.75 | 9894.75
TENDER ITEM TOTAL AMT OF UNDER GROUND TANK [ D ] | [6 empty] | Rs. | 3296551.3723 | 33572.1844 | 3330123.5567

## Report - Bill Summary
Civil Work for Ms SHAILY Engineering Plastics Ltd.
BILL SUMMARY
Sr. No. | Description | 1st RA | 2nd RA | 3rd RA | 4th RA | Cumulative
I | AS PER TENDER ITEM
A | FACTORY BUILDING | 3555741.3355 | 3995586.803 | 1669699.2734 | 6995684.093 | 16216711.5049 | 17464197.8123
B | SECURITY BUILDING |  |  |  |  | 0 | 0
C | SCRAP YARD |  |  |  |  | 0 | 0
D | UNDER GROUND TANK |  |  |  |  | 0 | 0
E | FIRE WATER TANK |  |  |  |  | 0 | 0
F | RCC ROAD & DRAIN | 1740311.269 | 1064376.615 | 0 | 138569.05 | 2943256.934 | 2997406.934
G | WATER SUPPLY NETWORK |  |  |  |  | 0 | 0
H | SEWAGE DISPOSAL NETWORK |  |  |  |  | 0 | 0
I | SEWAGE TREATMENT PLANT |  |  |  |  | 0 | 0
J | OPEN PARKING |  |  |  |  | 0
K | COMPOUND WALL |  |  |  |  | 0 | 0
L | ELECTRICAL PANEL ROOM |  |  |  |  | 0 | 0
M | EFFLUENT TREATMENT PLANT |  |  |  |  | 0 | 0
N | MISCELLANEOUS |  |  |  |  | 0 | 0
| Sub - Total (Tender Item) | 5296052.6045 | 5059963.418 | 1669699.2734 | 7134253.143 | 19159968.439
II | NON - TENDER ITEM / EXTRA ITEM
A | FACTORY BUILDING |  |  |  | 1247486.3074 | 1247486.3074
B | SECURITY BUILDING |  |  |  |  | 0
C | SCRAP YARD |  |  |  |  | 0
D | UNDER GROUND TANK |  |  |  |  | 0
E | FIRE WATER TANK |  |  |  |  | 0
F | RCC ROAD & DRAIN |  | 54150 | 0 |  | 54150
G | WATER SUPPLY NETWORK |  |  |  |  | 0
H | SEWAGE DISPOSAL NETWORK |  |  |  |  | 0
I | SEWAGE TREATMENT PLANT |  |  |  |  | 0
J | OPEN PARKING |  |  |  |  | 0
K | COMPOUND WALL |  |  |  |  | 0
L | ELECTRICAL PANEL ROOM |  |  |  |  | 0
M | EFFLUENT TREATMENT PLANT |  |  |  |  | 0
N | MISCELLANEOUS |  |  |  |  | 0
| Sub - Total (Extra Item) | 0 | 54150 | 0 | 1247486.3074 | 1301636.3074
| Sub Total (I + II) | 5296052.6045 | 5114113.418 | 1669699.2734 | 8381739.4503 | 20461604.7463
III | Add/Ded. for material rate diff. (-)
a | Basic Rate Diff. amount Cement | 0 |  |  |  | 0
b | Basic Rate Diff. amount Rein. Steel | -16695.5058 | -18559.0972 | -8940.1726 | -66168.186 | -110362.9616
c | Basic Rate Diff. amount Struc. Steel | 0 | 0 |  |  | 0
| Total Amount Rate Diff. | -16695.5058 | -18559.0972 | -8940.1726 | -66168.186 | -110362.9616
| CUMULATIVE AMOUNT | -16695.5058 | -35254.603
| Net Amount in Rs. | 5279357.0987 | 5095554.3209 | 1660759.1009 | 8315571.2643 | 20351241.7847
| CUMULATIVE AMOUNT | 5279357.0987 | 10374911.4196 | 12035670.5204 | 20351241.7847
| TOTAL AMOUNT | 5279357.0987 | 5095554.3209 | 1660759.1009 | 8315571.2643 | 20351241.7847
| i] Central Tax @ 9% on ( c ) | 475142.1389 | 458599.8889 | 149468.3191 | 748401.4138 | 1831611.7606
| ii] State Tax @ 9% on ( c ) | 475142.1389 | 458599.8889 | 149468.3191 | 748401.4138 | 1831611.7606
| TOTAL AMOUNT WITH GST | 6229641.3765 | 6012754.0986 | 1959695.739 | 9812374.0919 | 24014465.306
| i] Less:- Retention at 5% on ( c ) | -263967.8549 | -254777.716 | -83037.955 | -415778.5632 | -1017562.0892
| ii] Less:- Mobilization 10% on ( c ) | -527935.7099 | -509555.4321 | -166075.9101 | -831557.1264 | -2035124.1785
| DEDUCTION: ( - ) |  |  |  |  | 0
| NET PAYABLE AMOUNT | 5437737.8116 | 5248420.9505 | 1710581.8739 | 8565038.4022 | 20961779.0382
| CUMULATIVE NET AMOUNT | 5437737.8116 | 10686158.7621 | 12396740.636 | 20961779.0382